## Analog - Enhertu
Enhertu (T-DXd) — 2L+ HER2+ mBC (DESTINY-Breast03)
Sponsor: Daiichi Sankyo / AstraZeneca
Category | Milestone | Geography | Date | Lag from FDA (months) | Confidence | Source | Notes
Trial | Trial Primary Completion | US | 15 Mar 2022 | -4.7 | Known | ClinicalTrials.gov NCT03529110 | DESTINY-Breast03 primary analysis cutoff
Trial | Trial Data Readout | US | 19 Sep 2021 | -10.5 | Known | ESMO 2021 presentation | First presentation at ESMO Congress 2021
Regulatory | FDA Approval | US | 5 Aug 2022 |  | Known | FDA approval letter | Full approval for 2L+ HER2+ mBC based on DESTINY-Breast03
Regulatory | EMA Approval | France | 24 Jan 2023 | 5.6 | Known | EC decision — EMA EPAR | EMA centralized procedure; EC marketing authorization
Regulatory | EMA Approval | Germany | 24 Jan 2023 | 5.6 | Known | EC decision — EMA EPAR | Same EMA approval applies to all EU5
Regulatory | EMA Approval | Italy | 24 Jan 2023 | 5.6 | Known | EC decision — EMA EPAR
Regulatory | EMA Approval | Spain | 24 Jan 2023 | 5.6 | Known | EC decision — EMA EPAR
Regulatory | MHRA Approval | UK | 24 Jan 2023 | 5.6 | Known | MHRA GBR reliance procedure | MHRA followed EMA timeline via reliance pathway
Regulatory | Health Canada Approval | Canada | 17 Feb 2023 | 6.4 | Known | Health Canada NOC
Guidelines | NCCN Guideline Inclusion | US | 1 Sep 2022 | 0.9 | High | NCCN Breast Cancer v5.2022 | Category 1 preferred within ~1 month of FDA approval
Guidelines | NCCN Guideline Inclusion | Canada | 1 Sep 2022 | 0.9 | High | NCCN Breast Cancer v5.2022 | NCCN also referenced in Canadian practice
Guidelines | ESMO Guideline Inclusion | UK | 19 Oct 2021 | -9.5 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021 | T-DXd recommended as new standard 2L therapy for HER2+ mBC. Living Guideline format launched 11 May 2023.
Guidelines | ESMO Guideline Inclusion | France | 19 Oct 2021 | -9.5 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Germany | 19 Oct 2021 | -9.5 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Italy | 19 Oct 2021 | -9.5 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Spain | 19 Oct 2021 | -9.5 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
HTA / Reimbursement | NICE Final Appraisal | UK | 25 Oct 2023 | 14.7 | Known | NICE TA942 | Recommended for routine commissioning
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 2 Feb 2023 | 5.9 | Known | G-BA Beschluss — procedure 2022-08-01-D-836 | Considerable additional benefit. Decision 9 days after EMA approval.
HTA / Reimbursement | HAS Transparency Committee | France | 22 Feb 2023 | 6.6 | Known | HAS CT opinion — ENHERTU_22022023_AVIS_CT19944 | SMR: Important; ASMR III (moderate improvement). Published online 30 Mar 2023.
HTA / Reimbursement | AIFA Reimbursement | Italy | 3 Jul 2023 | 10.9 | Known | AIFA — GU Serie Generale n.153, 3 Jul 2023 | SSN reimbursement effective 4 Jul 2023. ~5 months post-EMA — faster than typical due to innovative drug status.
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 28 Oct 2022 | 2.8 | Known | CIPM financing decision — 28 Oct 2022 | SNS prescription available ~Dec 2022. Based on earlier EMA type II variation (Mar 2022), not Jan 2023 broadened indication.
HTA / Reimbursement | CADTH Recommendation | Canada | 29 Jun 2023 | 10.8 | High | CADTH pCODR recommendation | Recommended for reimbursement with clinical criteria
Commercial | Commercial Launch | US | 15 Aug 2022 | 0.3 | High | Daiichi Sankyo press release | US commercial launch within days of FDA approval
SoC Integration | SoC Integration | All | No data

## Analog - Trodelvy
Trodelvy (SG) — 3L+ mTNBC (ASCENT)
Sponsor: Gilead Sciences
Category | Milestone | Geography | Date | Lag from FDA (months) | Confidence | Source | Notes
Trial | Trial Primary Completion | US | 1 Nov 2020 | -5.2 | High | ClinicalTrials.gov NCT02574455 | ASCENT trial primary completion
Trial | Trial Data Readout | US | 19 Sep 2020 | -6.6 | Known | ESMO 2020 — NEJM publication | Primary results presented at ESMO Virtual 2020
Regulatory | FDA Approval | US | 7 Apr 2021 |  | Known | FDA approval letter | Regular approval for 3L+ mTNBC (accelerated approval Apr 2020 converted)
Regulatory | EMA Approval | France | 10 Nov 2021 | 7.1 | Known | EC decision — EMA EPAR | EMA centralized procedure; ~7 months post-FDA
Regulatory | EMA Approval | Germany | 10 Nov 2021 | 7.1 | Known | EC decision — EMA EPAR
Regulatory | EMA Approval | Italy | 10 Nov 2021 | 7.1 | Known | EC decision — EMA EPAR
Regulatory | EMA Approval | Spain | 10 Nov 2021 | 7.1 | Known | EC decision — EMA EPAR
Regulatory | MHRA Approval | UK | 15 Dec 2021 | 8.3 | High | MHRA approval | MHRA followed shortly after EMA; approximate date
Regulatory | Health Canada Approval | Canada | 18 Jul 2022 | 15.4 | Known | Health Canada NOC | ~15 months post-FDA
Guidelines | NCCN Guideline Inclusion | US | 1 May 2021 | 0.8 | High | NCCN Breast Cancer v4.2021 | Added within one update cycle of full approval
Guidelines | NCCN Guideline Inclusion | Canada | 1 May 2021 | 0.8 | High | NCCN Breast Cancer v4.2021
Guidelines | ESMO Guideline Inclusion | UK | 19 Oct 2021 | 6.4 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021 | SG recommended as preferred treatment after anthracyclines and taxanes for mTNBC.
Guidelines | ESMO Guideline Inclusion | France | 19 Oct 2021 | 6.4 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Germany | 19 Oct 2021 | 6.4 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Italy | 19 Oct 2021 | 6.4 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
Guidelines | ESMO Guideline Inclusion | Spain | 19 Oct 2021 | 6.4 | Known | ESMO CPG — Annals of Oncology, 19 Oct 2021
HTA / Reimbursement | NICE Final Appraisal | UK | 12 Jul 2023 | 27.2 | Known | NICE TA900 | Recommended via Cancer Drugs Fund; ~27 months post-FDA
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 19 May 2022 | 13.4 | Known | G-BA Beschluss — procedure 2021-12-01-D-750 | ~6 months post-EMA approval.
HTA / Reimbursement | HAS Transparency Committee | France | 6 Apr 2022 | 12.0 | Known | HAS CT opinion — TRODELVY_06042022_AVIS_CT19684 | SMR: Important; ASMR III (moderate improvement). Published online 2 Jun 2022.
HTA / Reimbursement | AIFA Reimbursement | Italy | 9 Aug 2022 | 16.1 | Known | AIFA — GU Serie Generale n.185, 9 Aug 2022 | SSN reimbursement effective 10 Aug 2022. Access via Fund for Innovative Drugs. ~9 months post-EMA.
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 28 Oct 2022 | 18.7 | Known | CIPM financing decision — 28 Oct 2022 | Same CIPM session approved both Trodelvy and Enhertu. SNS prescription available ~Dec 2022. ~12 months post-EMA.
HTA / Reimbursement | CADTH Recommendation | Canada | 1 Oct 2022 | 17.8 | Moderate | CADTH pCODR recommendation | Approximate date; ~18 months post-FDA
Commercial | Commercial Launch | US | 15 Apr 2021 | 0.3 | High | Gilead press release | US launch shortly after FDA approval
SoC Integration | SoC Integration | All | No data

## Derived Lags
Derived Lag Analysis (months from FDA approval)
Milestone | Geography | Enhertu Lag (months) | Trodelvy 3L+ Lag (months) | Optimistic | Base (Mid) | Conservative | Notes
EMA Approval | France | 5.6 | 7.1 | 5.6 | 6.3 | 7.1
EMA Approval | Germany | 5.6 | 7.1 | 5.6 | 6.3 | 7.1
EMA Approval | Italy | 5.6 | 7.1 | 5.6 | 6.3 | 7.1
EMA Approval | Spain | 5.6 | 7.1 | 5.6 | 6.3 | 7.1
MHRA Approval | UK | 5.6 | 8.3 | 5.6 | 7.0 | 8.3
Health Canada Approval | Canada | 6.4 | 15.4 | 6.4 | 10.9 | 15.4
NCCN Guideline Inclusion | US | 0.9 | 0.8 | 0.8 | 0.9 | 0.9
NCCN Guideline Inclusion | Canada | 0.9 | 0.8 | 0.8 | 0.9 | 0.9
ESMO Guideline Inclusion | UK | -9.5 | 6.4 | -9.5 | -1.5 | 6.4
ESMO Guideline Inclusion | France | -9.5 | 6.4 | -9.5 | -1.5 | 6.4
ESMO Guideline Inclusion | Germany | -9.5 | 6.4 | -9.5 | -1.5 | 6.4
ESMO Guideline Inclusion | Italy | -9.5 | 6.4 | -9.5 | -1.5 | 6.4
ESMO Guideline Inclusion | Spain | -9.5 | 6.4 | -9.5 | -1.5 | 6.4
NICE Final Appraisal | UK | 14.7 | 27.2 | 14.7 | 20.9 | 27.2
G-BA Benefit Assessment | Germany | 5.9 | 13.4 | 5.9 | 9.7 | 13.4
HAS Transparency Committee | France | 6.6 | 12.0 | 6.6 | 9.3 | 12.0
AIFA Reimbursement | Italy | 10.9 | 16.1 | 10.9 | 13.5 | 16.1
AEMPS Pricing & Reimbursement | Spain | 2.8 | 18.7 | 2.8 | 10.8 | 18.7
CADTH Recommendation | Canada | 10.8 | 17.8 | 10.8 | 14.3 | 17.8
Commercial Launch | US | 0.3 | 0.3 | 0.3 | 0.3 | 0.3

## Trodelvy 1L CPS<10 (ASCENT-03)
Trodelvy (SG) — 1L mTNBC (BRCA-wt, PD-L1 CPS<10) (ASCENT-03)
Sponsor: Gilead Sciences
Category | Milestone | Geography | Optimistic | Base | Conservative | Confidence | Source / Basis | Notes
Trial | Trial Primary Completion | US | 1 Jul 2028 | 1 Jul 2028 | 1 Jul 2028 | Known | ClinicalTrials.gov NCT05382299 — registered PCD | Registered PCD Jul 2028 is for final OS analysis. PFS interim already read out.
Trial | Trial Data Readout | US | 1 Dec 2025 | 1 Dec 2025 | 1 Dec 2025 | High | Gilead presentations / regulatory submission | PFS data already presented; supports sBLA filing. Trial status: Active, Not Recruiting (623 enrolled).
Regulatory | FDA Approval | US | 1 Sep 2026 | 1 Sep 2026 | 1 Sep 2026 | High | Gilead guidance: accelerated 1L launch H2 2026 | Assumes standard sBLA review (~6-8 months) or Priority Review (~6 months)
Regulatory | EMA Approval | France | 18 Feb 2027 | 11 Mar 2027 | 5 Apr 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-09-01 + 6.3 months
Regulatory | EMA Approval | Germany | 18 Feb 2027 | 11 Mar 2027 | 5 Apr 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-09-01 + 6.3 months
Regulatory | EMA Approval | Italy | 18 Feb 2027 | 11 Mar 2027 | 5 Apr 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-09-01 + 6.3 months
Regulatory | EMA Approval | Spain | 18 Feb 2027 | 11 Mar 2027 | 5 Apr 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-09-01 + 6.3 months
Regulatory | MHRA Approval | UK | 18 Feb 2027 | 2 Apr 2027 | 11 May 2027 | Moderate | Analog-based projection (base): 7.0 months post-FDA | Projected from FDA approval 2026-09-01 + 7.0 months
Regulatory | Health Canada Approval | Canada | 14 Mar 2027 | 29 Jul 2027 | 13 Dec 2027 | Moderate | Analog-based projection (base): 10.9 months post-FDA | Projected from FDA approval 2026-09-01 + 10.9 months
Guidelines | NCCN Guideline Inclusion | US | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026 | Category 1 preferred 1L mTNBC BRCA-wt/PD-L1 CPS<10 — listed AHEAD of approval
Guidelines | NCCN Guideline Inclusion | Canada | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026 | NCCN also referenced in Canadian practice
Guidelines | ESMO Guideline Inclusion | UK | 16 Nov 2025 | 18 Jul 2026 | 14 Mar 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-09-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | France | 16 Nov 2025 | 18 Jul 2026 | 14 Mar 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-09-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Germany | 16 Nov 2025 | 18 Jul 2026 | 14 Mar 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-09-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Italy | 16 Nov 2025 | 18 Jul 2026 | 14 Mar 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-09-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Spain | 16 Nov 2025 | 18 Jul 2026 | 14 Mar 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-09-01 + -1.5 months
HTA / Reimbursement | NICE Final Appraisal | UK | 22 Nov 2027 | 29 May 2028 | 6 Dec 2028 | Moderate | Analog-based projection (base): 20.9 months post-FDA | Projected from FDA approval 2026-09-01 + 20.9 months
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 27 Feb 2027 | 23 Jun 2027 | 13 Oct 2027 | Moderate | Analog-based projection (base): 9.7 months post-FDA | Projected from FDA approval 2026-09-01 + 9.7 months
HTA / Reimbursement | HAS Transparency Committee | France | 20 Mar 2027 | 11 Jun 2027 | 1 Sep 2027 | Moderate | Analog-based projection (base): 9.3 months post-FDA | Projected from FDA approval 2026-09-01 + 9.3 months
HTA / Reimbursement | AIFA Reimbursement | Italy | 29 Jul 2027 | 16 Oct 2027 | 4 Jan 2028 | Moderate | Analog-based projection (base): 13.5 months post-FDA | Projected from FDA approval 2026-09-01 + 13.5 months
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 25 Nov 2026 | 26 Jul 2027 | 23 Mar 2028 | Moderate | Analog-based projection (base): 10.8 months post-FDA | Projected from FDA approval 2026-09-01 + 10.8 months
HTA / Reimbursement | CADTH Recommendation | Canada | 26 Jul 2027 | 10 Nov 2027 | 24 Feb 2028 | Moderate | Analog-based projection (base): 14.3 months post-FDA | Projected from FDA approval 2026-09-01 + 14.3 months
Commercial | Commercial Launch | US | 1 Oct 2026 | 1 Oct 2026 | 1 Oct 2026 | High | Gilead guidance: accelerated launch H2 2026 | Targeting rapid launch post-approval
SoC Integration | SoC Integration | US | 1 Oct 2026 | 1 Oct 2026 | 1 Oct 2026 | Low | Derived: max(guideline, reimbursement/access) | US SoC = max(NCCN 2026-01-15, launch 2026-10-01)
SoC Integration | SoC Integration | UK | 22 Nov 2027 | 29 May 2028 | 6 Dec 2028 | Low | Derived: max(guideline, reimbursement/access) | UK SoC = max(guideline 2026-07-18, HTA 2028-05-29)
SoC Integration | SoC Integration | France | 20 Mar 2027 | 11 Jun 2027 | 1 Sep 2027 | Low | Derived: max(guideline, reimbursement/access) | France SoC = max(guideline 2026-07-18, HTA 2027-06-11)
SoC Integration | SoC Integration | Germany | 18 Feb 2027 | 11 Mar 2027 | 5 Apr 2027 | Low | Derived: max(guideline, reimbursement/access) | DE SoC = max(ESMO 2026-07-18, EMA 2027-03-11). G-BA does not gate access.
SoC Integration | SoC Integration | Italy | 29 Jul 2027 | 16 Oct 2027 | 4 Jan 2028 | Low | Derived: max(guideline, reimbursement/access) | Italy SoC = max(guideline 2026-07-18, HTA 2027-10-16)
SoC Integration | SoC Integration | Spain | 25 Nov 2026 | 26 Jul 2027 | 23 Mar 2028 | Low | Derived: max(guideline, reimbursement/access) | Spain SoC = max(guideline 2026-07-18, HTA 2027-07-26)
SoC Integration | SoC Integration | Canada | 26 Jul 2027 | 10 Nov 2027 | 24 Feb 2028 | Low | Derived: max(guideline, reimbursement/access) | Canada SoC = max(guideline 2026-01-15, HTA 2027-11-10)

## Trodelvy 1L CPS>=10 (ASCENT-04)
Trodelvy (SG) + Keytruda — 1L mTNBC (PD-L1 CPS>=10) (ASCENT-04)
Sponsor: Gilead Sciences
Category | Milestone | Geography | Optimistic | Base | Conservative | Confidence | Source / Basis | Notes
Trial | Trial Primary Completion | US | 1 Feb 2027 | 1 Feb 2027 | 1 Feb 2027 | Known | ClinicalTrials.gov NCT05382286 — registered PCD | Registered PCD Feb 2027 is for final OS analysis. PFS data published NEJM 21 Jan 2026.
Trial | Trial Data Readout | US | 21 Jan 2026 | 21 Jan 2026 | 21 Jan 2026 | Known | NEJM publication — 21 Jan 2026 | Full ASCENT-04 PFS dataset published; supported NCCN Category 1 upgrade. Trial: Active, Not Recruiting (443 enrolled).
Regulatory | FDA Approval | US | 1 Oct 2026 | 1 Oct 2026 | 1 Oct 2026 | High | Projected based on Gilead H2 2026 launch target | May come slightly after ASCENT-03 monotherapy approval
Regulatory | EMA Approval | France | 20 Mar 2027 | 10 Apr 2027 | 5 May 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-10-01 + 6.3 months
Regulatory | EMA Approval | Germany | 20 Mar 2027 | 10 Apr 2027 | 5 May 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-10-01 + 6.3 months
Regulatory | EMA Approval | Italy | 20 Mar 2027 | 10 Apr 2027 | 5 May 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-10-01 + 6.3 months
Regulatory | EMA Approval | Spain | 20 Mar 2027 | 10 Apr 2027 | 5 May 2027 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2026-10-01 + 6.3 months
Regulatory | MHRA Approval | UK | 20 Mar 2027 | 2 May 2027 | 10 Jun 2027 | Moderate | Analog-based projection (base): 7.0 months post-FDA | Projected from FDA approval 2026-10-01 + 7.0 months
Regulatory | Health Canada Approval | Canada | 13 Apr 2027 | 28 Aug 2027 | 12 Jan 2028 | Moderate | Analog-based projection (base): 10.9 months post-FDA | Projected from FDA approval 2026-10-01 + 10.9 months
Guidelines | NCCN Guideline Inclusion | US | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026 | Initially Category 2A preferred; upgraded to Category 1 in v2.2026
Guidelines | NCCN Guideline Inclusion | Canada | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026
Guidelines | ESMO Guideline Inclusion | UK | 16 Dec 2025 | 17 Aug 2026 | 13 Apr 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-10-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | France | 16 Dec 2025 | 17 Aug 2026 | 13 Apr 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-10-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Germany | 16 Dec 2025 | 17 Aug 2026 | 13 Apr 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-10-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Italy | 16 Dec 2025 | 17 Aug 2026 | 13 Apr 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-10-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Spain | 16 Dec 2025 | 17 Aug 2026 | 13 Apr 2027 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-10-01 + -1.5 months
HTA / Reimbursement | NICE Final Appraisal | UK | 22 Dec 2027 | 28 Jun 2028 | 5 Jan 2029 | Moderate | Analog-based projection (base): 20.9 months post-FDA | Projected from FDA approval 2026-10-01 + 20.9 months
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 29 Mar 2027 | 23 Jul 2027 | 12 Nov 2027 | Moderate | Analog-based projection (base): 9.7 months post-FDA | Projected from FDA approval 2026-10-01 + 9.7 months
HTA / Reimbursement | HAS Transparency Committee | France | 19 Apr 2027 | 11 Jul 2027 | 1 Oct 2027 | Moderate | Analog-based projection (base): 9.3 months post-FDA | Projected from FDA approval 2026-10-01 + 9.3 months
HTA / Reimbursement | AIFA Reimbursement | Italy | 28 Aug 2027 | 15 Nov 2027 | 3 Feb 2028 | Moderate | Analog-based projection (base): 13.5 months post-FDA | Projected from FDA approval 2026-10-01 + 13.5 months
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 25 Dec 2026 | 25 Aug 2027 | 22 Apr 2028 | Moderate | Analog-based projection (base): 10.8 months post-FDA | Projected from FDA approval 2026-10-01 + 10.8 months
HTA / Reimbursement | CADTH Recommendation | Canada | 25 Aug 2027 | 10 Dec 2027 | 25 Mar 2028 | Moderate | Analog-based projection (base): 14.3 months post-FDA | Projected from FDA approval 2026-10-01 + 14.3 months
Commercial | Commercial Launch | US | 1 Nov 2026 | 1 Nov 2026 | 1 Nov 2026 | High | Gilead guidance: accelerated launch H2 2026 | Combo launch may follow monotherapy by ~1 month
SoC Integration | SoC Integration | US | 1 Nov 2026 | 1 Nov 2026 | 1 Nov 2026 | Low | Derived: max(guideline, reimbursement/access) | US SoC = max(NCCN 2026-01-15, launch 2026-11-01)
SoC Integration | SoC Integration | UK | 22 Dec 2027 | 28 Jun 2028 | 5 Jan 2029 | Low | Derived: max(guideline, reimbursement/access) | UK SoC = max(guideline 2026-08-17, HTA 2028-06-28)
SoC Integration | SoC Integration | France | 19 Apr 2027 | 11 Jul 2027 | 1 Oct 2027 | Low | Derived: max(guideline, reimbursement/access) | France SoC = max(guideline 2026-08-17, HTA 2027-07-11)
SoC Integration | SoC Integration | Germany | 20 Mar 2027 | 10 Apr 2027 | 5 May 2027 | Low | Derived: max(guideline, reimbursement/access) | DE SoC = max(ESMO 2026-08-17, EMA 2027-04-10). G-BA does not gate access.
SoC Integration | SoC Integration | Italy | 28 Aug 2027 | 15 Nov 2027 | 3 Feb 2028 | Low | Derived: max(guideline, reimbursement/access) | Italy SoC = max(guideline 2026-08-17, HTA 2027-11-15)
SoC Integration | SoC Integration | Spain | 25 Dec 2026 | 25 Aug 2027 | 22 Apr 2028 | Low | Derived: max(guideline, reimbursement/access) | Spain SoC = max(guideline 2026-08-17, HTA 2027-08-25)
SoC Integration | SoC Integration | Canada | 25 Aug 2027 | 10 Dec 2027 | 25 Mar 2028 | Low | Derived: max(guideline, reimbursement/access) | Canada SoC = max(guideline 2026-01-15, HTA 2027-12-10)

## Dato-DXd 1L CPS<10 (TB02)
Dato-DXd (Datroway) — 1L mTNBC (BRCA-wt, PD-L1 CPS<10) (TROPION-Breast02)
Sponsor: Daiichi Sankyo / AstraZeneca
Category | Milestone | Geography | Optimistic | Base | Conservative | Confidence | Source / Basis | Notes
Trial | Trial Primary Completion | US | 1 Mar 2025 | 1 Mar 2025 | 1 Mar 2025 | Moderate | ClinicalTrials.gov NCT05104866 (estimated) | TROPION-Breast02 primary completion estimate
Trial | Trial Data Readout | US | 1 Jun 2025 | 1 Jun 2025 | 1 Jun 2025 | High | Data presented at major congress | Primary data supported sBLA submission
Regulatory | FDA Approval | US | 1 Jun 2026 | 1 Jun 2026 | 1 Jun 2026 | High | PDUFA Q2 2026 under Priority Review | Priority Review granted Feb 2026; PDUFA target date Q2 2026
Regulatory | EMA Approval | France | 1 Sep 2026 | 1 Sep 2026 | 1 Sep 2026 | Moderate | Daiichi Q3 FY2025 Earnings
Regulatory | EMA Approval | Germany | 1 Sep 2026 | 1 Sep 2026 | 1 Sep 2026 | Moderate | Daiichi Q3 FY2025 Earnings: EU approval projected Q3 2026 | Based on regulatory submission accepted Dec 2025
Regulatory | EMA Approval | Italy | 1 Sep 2026 | 1 Sep 2026 | 1 Sep 2026 | Moderate | Daiichi Q3 FY2025 Earnings
Regulatory | EMA Approval | Spain | 1 Sep 2026 | 1 Sep 2026 | 1 Sep 2026 | Moderate | Daiichi Q3 FY2025 Earnings
Regulatory | MHRA Approval | UK | 18 Nov 2026 | 31 Dec 2026 | 8 Feb 2027 | Moderate | Analog-based projection (base): 7.0 months post-FDA | Projected from FDA approval 2026-06-01 + 7.0 months
Regulatory | Health Canada Approval | Canada | 12 Dec 2026 | 28 Apr 2027 | 12 Sep 2027 | Moderate | Analog-based projection (base): 10.9 months post-FDA | Projected from FDA approval 2026-06-01 + 10.9 months
Guidelines | NCCN Guideline Inclusion | US | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026 | Category 2A other recommended; upgraded to Category 2A preferred in v2.2026
Guidelines | NCCN Guideline Inclusion | Canada | 15 Jan 2026 | 15 Jan 2026 | 15 Jan 2026 | Known | NCCN Breast Cancer v1.2026
Guidelines | ESMO Guideline Inclusion | UK | 16 Aug 2025 | 17 Apr 2026 | 12 Dec 2026 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-06-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | France | 16 Aug 2025 | 17 Apr 2026 | 12 Dec 2026 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-06-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Germany | 16 Aug 2025 | 17 Apr 2026 | 12 Dec 2026 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-06-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Italy | 16 Aug 2025 | 17 Apr 2026 | 12 Dec 2026 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-06-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Spain | 16 Aug 2025 | 17 Apr 2026 | 12 Dec 2026 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2026-06-01 + -1.5 months
HTA / Reimbursement | NICE Final Appraisal | UK | 22 Aug 2027 | 27 Feb 2028 | 5 Sep 2028 | Moderate | Analog-based projection (base): 20.9 months post-FDA | Projected from FDA approval 2026-06-01 + 20.9 months
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 27 Nov 2026 | 23 Mar 2027 | 13 Jul 2027 | Moderate | Analog-based projection (base): 9.7 months post-FDA | Projected from FDA approval 2026-06-01 + 9.7 months
HTA / Reimbursement | HAS Transparency Committee | France | 18 Dec 2026 | 11 Mar 2027 | 1 Jun 2027 | Moderate | Analog-based projection (base): 9.3 months post-FDA | Projected from FDA approval 2026-06-01 + 9.3 months
HTA / Reimbursement | AIFA Reimbursement | Italy | 28 Apr 2027 | 16 Jul 2027 | 4 Oct 2027 | Moderate | Analog-based projection (base): 13.5 months post-FDA | Projected from FDA approval 2026-06-01 + 13.5 months
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 25 Aug 2026 | 25 Apr 2027 | 22 Dec 2027 | Moderate | Analog-based projection (base): 10.8 months post-FDA | Projected from FDA approval 2026-06-01 + 10.8 months
HTA / Reimbursement | CADTH Recommendation | Canada | 25 Apr 2027 | 10 Aug 2027 | 24 Nov 2027 | Moderate | Analog-based projection (base): 14.3 months post-FDA | Projected from FDA approval 2026-06-01 + 14.3 months
Commercial | Commercial Launch | US | 1 Jul 2026 | 1 Jul 2026 | 1 Jul 2026 | High | Projected post-PDUFA | Expected rapid US launch following FDA approval
SoC Integration | SoC Integration | US | 1 Jul 2026 | 1 Jul 2026 | 1 Jul 2026 | Low | Derived: max(guideline, reimbursement/access) | US SoC = max(NCCN 2026-01-15, launch 2026-07-01)
SoC Integration | SoC Integration | UK | 22 Aug 2027 | 27 Feb 2028 | 5 Sep 2028 | Low | Derived: max(guideline, reimbursement/access) | UK SoC = max(guideline 2026-04-17, HTA 2028-02-27)
SoC Integration | SoC Integration | France | 18 Dec 2026 | 11 Mar 2027 | 1 Jun 2027 | Low | Derived: max(guideline, reimbursement/access) | France SoC = max(guideline 2026-04-17, HTA 2027-03-11)
SoC Integration | SoC Integration | Germany | 1 Sep 2026 | 1 Sep 2026 | 12 Dec 2026 | Low | Derived: max(guideline, reimbursement/access) | DE SoC = max(ESMO 2026-04-17, EMA 2026-09-01). G-BA does not gate access.
SoC Integration | SoC Integration | Italy | 28 Apr 2027 | 16 Jul 2027 | 4 Oct 2027 | Low | Derived: max(guideline, reimbursement/access) | Italy SoC = max(guideline 2026-04-17, HTA 2027-07-16)
SoC Integration | SoC Integration | Spain | 25 Aug 2026 | 25 Apr 2027 | 22 Dec 2027 | Low | Derived: max(guideline, reimbursement/access) | Spain SoC = max(guideline 2026-04-17, HTA 2027-04-25)
SoC Integration | SoC Integration | Canada | 25 Apr 2027 | 10 Aug 2027 | 24 Nov 2027 | Low | Derived: max(guideline, reimbursement/access) | Canada SoC = max(guideline 2026-01-15, HTA 2027-08-10)

## Dato-DXd 1L CPS>=10 (TB05)
Dato-DXd (Datroway) +/- Durvalumab — 1L mTNBC (PD-L1 CPS>=10) (TROPION-Breast05)
Sponsor: Daiichi Sankyo / AstraZeneca
Category | Milestone | Geography | Optimistic | Base | Conservative | Confidence | Source / Basis | Notes
Trial | Trial Primary Completion | US | 28 Jul 2027 | 28 Jul 2027 | 28 Jul 2027 | Known | ClinicalTrials.gov NCT06103864 — registered PCD | TROPION-Breast05. Status: Recruiting. Study completion: Sep 2030.
Trial | Trial Data Readout | US | 1 Mar 2028 | 1 Mar 2028 | 1 Mar 2028 | Low | Estimated: ~5 months post-PCD for major congress presentation | Assumes data maturation + congress cycle
Regulatory | FDA Approval | US | 1 Jan 2029 | 1 Jan 2029 | 1 Jan 2029 | Low | Projected: ~6-10 months post-submission | Assumes standard or Priority Review
Regulatory | EMA Approval | France | 20 Jun 2029 | 11 Jul 2029 | 5 Aug 2029 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2029-01-01 + 6.3 months
Regulatory | EMA Approval | Germany | 20 Jun 2029 | 11 Jul 2029 | 5 Aug 2029 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2029-01-01 + 6.3 months
Regulatory | EMA Approval | Italy | 20 Jun 2029 | 11 Jul 2029 | 5 Aug 2029 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2029-01-01 + 6.3 months
Regulatory | EMA Approval | Spain | 20 Jun 2029 | 11 Jul 2029 | 5 Aug 2029 | Moderate | Analog-based projection (base): 6.3 months post-FDA | Projected from FDA approval 2029-01-01 + 6.3 months
Regulatory | MHRA Approval | UK | 20 Jun 2029 | 2 Aug 2029 | 10 Sep 2029 | Moderate | Analog-based projection (base): 7.0 months post-FDA | Projected from FDA approval 2029-01-01 + 7.0 months
Regulatory | Health Canada Approval | Canada | 14 Jul 2029 | 28 Nov 2029 | 14 Apr 2030 | Moderate | Analog-based projection (base): 10.9 months post-FDA | Projected from FDA approval 2029-01-01 + 10.9 months
Guidelines | NCCN Guideline Inclusion | US | 25 Jan 2029 | 28 Jan 2029 | 28 Jan 2029 | Moderate | Analog-based projection (base): 0.9 months post-FDA | Projected from FDA approval 2029-01-01 + 0.9 months
Guidelines | NCCN Guideline Inclusion | Canada | 25 Jan 2029 | 28 Jan 2029 | 28 Jan 2029 | Moderate | Analog-based projection (base): 0.9 months post-FDA | Projected from FDA approval 2029-01-01 + 0.9 months
Guidelines | ESMO Guideline Inclusion | UK | 18 Mar 2028 | 17 Nov 2028 | 14 Jul 2029 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2029-01-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | France | 18 Mar 2028 | 17 Nov 2028 | 14 Jul 2029 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2029-01-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Germany | 18 Mar 2028 | 17 Nov 2028 | 14 Jul 2029 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2029-01-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Italy | 18 Mar 2028 | 17 Nov 2028 | 14 Jul 2029 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2029-01-01 + -1.5 months
Guidelines | ESMO Guideline Inclusion | Spain | 18 Mar 2028 | 17 Nov 2028 | 14 Jul 2029 | Moderate | Analog-based projection (base): -1.5 months post-FDA | Projected from FDA approval 2029-01-01 + -1.5 months
HTA / Reimbursement | NICE Final Appraisal | UK | 24 Mar 2030 | 29 Sep 2030 | 8 Apr 2031 | Moderate | Analog-based projection (base): 20.9 months post-FDA | Projected from FDA approval 2029-01-01 + 20.9 months
HTA / Reimbursement | G-BA Benefit Assessment | Germany | 29 Jun 2029 | 23 Oct 2029 | 12 Feb 2030 | Moderate | Analog-based projection (base): 9.7 months post-FDA | Projected from FDA approval 2029-01-01 + 9.7 months
HTA / Reimbursement | HAS Transparency Committee | France | 20 Jul 2029 | 11 Oct 2029 | 1 Jan 2030 | Moderate | Analog-based projection (base): 9.3 months post-FDA | Projected from FDA approval 2029-01-01 + 9.3 months
HTA / Reimbursement | AIFA Reimbursement | Italy | 28 Nov 2029 | 15 Feb 2030 | 6 May 2030 | Moderate | Analog-based projection (base): 13.5 months post-FDA | Projected from FDA approval 2029-01-01 + 13.5 months
HTA / Reimbursement | AEMPS Pricing & Reimbursement | Spain | 27 Mar 2029 | 25 Nov 2029 | 24 Jul 2030 | Moderate | Analog-based projection (base): 10.8 months post-FDA | Projected from FDA approval 2029-01-01 + 10.8 months
HTA / Reimbursement | CADTH Recommendation | Canada | 25 Nov 2029 | 12 Mar 2030 | 26 Jun 2030 | Moderate | Analog-based projection (base): 14.3 months post-FDA | Projected from FDA approval 2029-01-01 + 14.3 months
Commercial | Commercial Launch | US | 1 Feb 2029 | 1 Feb 2029 | 1 Feb 2029 | Low | Projected post-FDA approval
SoC Integration | SoC Integration | US | 1 Feb 2029 | 1 Feb 2029 | 1 Feb 2029 | Low | Derived: max(guideline, reimbursement/access) | US SoC = max(NCCN 2029-01-28, launch 2029-02-01)
SoC Integration | SoC Integration | UK | 24 Mar 2030 | 29 Sep 2030 | 8 Apr 2031 | Low | Derived: max(guideline, reimbursement/access) | UK SoC = max(guideline 2028-11-17, HTA 2030-09-29)
SoC Integration | SoC Integration | France | 20 Jul 2029 | 11 Oct 2029 | 1 Jan 2030 | Low | Derived: max(guideline, reimbursement/access) | France SoC = max(guideline 2028-11-17, HTA 2029-10-11)
SoC Integration | SoC Integration | Germany | 20 Jun 2029 | 11 Jul 2029 | 5 Aug 2029 | Low | Derived: max(guideline, reimbursement/access) | DE SoC = max(ESMO 2028-11-17, EMA 2029-07-11). G-BA does not gate access.
SoC Integration | SoC Integration | Italy | 28 Nov 2029 | 15 Feb 2030 | 6 May 2030 | Low | Derived: max(guideline, reimbursement/access) | Italy SoC = max(guideline 2028-11-17, HTA 2030-02-15)
SoC Integration | SoC Integration | Spain | 27 Mar 2029 | 25 Nov 2029 | 24 Jul 2030 | Low | Derived: max(guideline, reimbursement/access) | Spain SoC = max(guideline 2028-11-17, HTA 2029-11-25)
SoC Integration | SoC Integration | Canada | 25 Nov 2029 | 12 Mar 2030 | 26 Jun 2030 | Low | Derived: max(guideline, reimbursement/access) | Canada SoC = max(guideline 2029-01-28, HTA 2030-03-12)

## Assumptions & Gaps
Assumptions & Data Gaps Log
ID | Category | Description | Impact | Status | Related Drug | Data Gap? | Action Required
M001 | Methodology | FDA approval date is used as T=0 anchor for all market-relative lag projections. | High | Active | General | No
M002 | Methodology | Two analogs bracket the projection range: Enhertu 2L+ HER2+ mBC (optimistic) and Trodelvy 3L+ mTNBC (conservative). | High | Active | General | No
M003 | Methodology | SoC integration is defined as the LATER of (a) guideline inclusion and (b) national reimbursement/access. | High | Active | General | No
M004 | Methodology | For Germany, SoC integration uses EMA approval date (not G-BA) as access is available during free-pricing period under AMNOG. | Medium | Active | General | No
M005 | Methodology | For US, SoC integration = max(NCCN guideline inclusion, commercial launch date). No HTA gate. | Medium | Active | General | No
R001 | Regulatory | EMA centralized procedure assumed for all EU5 markets; no national divergence. | Medium | Active | General | No
R002 | Regulatory | MHRA assumed to follow EMA via Great Britain reliance pathway, adding 0-2 months to EMA date. | Low | Active | General | No
R003 | Regulatory | Health Canada assumed to run parallel review; typically 6-15 months post-FDA based on analogs. | Medium | Active | General | No
R004 | Regulatory | Dato-DXd (TROPION-Breast02) PDUFA target Q2 2026 based on FDA Priority Review grant Feb 2026. | High | Active | Dato-DXd | No
R005 | Regulatory | Trodelvy 1L (ASCENT-03) FDA approval targeted H2 2026 based on Gilead Q4 2025 Earnings guidance for accelerated launch. | High | Active | Trodelvy | No
R006 | Regulatory | Trodelvy 1L (ASCENT-04 combo) FDA approval expected H2 2026, possibly 1-2 months after ASCENT-03 monotherapy. | Medium | Active | Trodelvy | No
R007 | Regulatory | Dato-DXd EU/China approval projected as early as Q3 2026 per Daiichi Q3 FY2025 Earnings guidance, based on regulatory submission accepted Dec 2025. | High | Active | Dato-DXd | No
T001 | Trial | TROPION-Breast05 (NCT06103864) registered PCD is Jul 28, 2027. Status: Recruiting. Study completion Sep 2030. Confirmed via ClinicalTrials.gov API. | High | Resolved | Dato-DXd | No
T002 | Trial | ASCENT-03 (NCT05382299) registered PCD Jul 2028; ASCENT-04 (NCT05382286) registered PCD Feb 2027. Both are final OS analysis dates — PFS data already presented. Note: original NCT numbers in data were swapped, now corrected. Confirmed via ClinicalTrials.gov API. | Medium | Resolved | Trodelvy | No
G001 | Guideline | NCCN already lists both Trodelvy and Dato-DXd for 1L mTNBC pre-approval (v1.2026 and v2.2026). NCCN guideline milestone is therefore BEFORE FDA approval — unusual but confirmed. | High | Active | General | No
G002 | Guideline | ESMO guideline inclusion for 1L TNBC ADCs assumed to follow within 6-12 months of FDA approval, based on analog precedent. | Medium | Active | General | No
G003 | Guideline | Trodelvy Category 1 vs Dato-DXd Category 2A reflects greater evidence maturity (inc. OS data in 2L), not lack of support for Dato-DXd. | Medium | Active | General | No
H001 | Reimbursement | NICE appraisal timelines assumed 12-28 months post-FDA based on analogs. CDF route possible for Dato-DXd given weaker evidence vs Trodelvy. | High | Active | General | No
H002 | Reimbursement | G-BA AMNOG assessment assumed within 3-6 months of EMA approval; does not gate market access in Germany. | Medium | Active | General | No
H003 | Reimbursement | HAS (France) transparency committee opinion assumed 8-17 months post-FDA; pricing negotiation adds further time. | Medium | Active | General | No
H004 | Reimbursement | AIFA (Italy) reimbursement assumed 18-24 months post-FDA; typically slowest EU5 market. | Medium | Active | General | No
H005 | Reimbursement | AEMPS/Spain reimbursement assumed 20-27 months post-FDA; national + regional pricing layers add variability. | Medium | Active | General | No
H006 | Reimbursement | CADTH/pCODR (Canada) recommendation assumed 12-20 months post-FDA; provincial listing adds further time. | Medium | Active | General | No
GAP001 | Data Gap | HAS (France) decision dates confirmed: Enhertu CT opinion 22 Feb 2023, Trodelvy CT opinion 6 Apr 2022. Sourced from has-sante.fr. | Medium | Resolved | General | No
GAP002 | Data Gap | AIFA (Italy) dates confirmed: Enhertu GU n.153 on 3 Jul 2023 (~5 months post-EMA); Trodelvy GU n.185 on 9 Aug 2022 (~9 months post-EMA). Sourced from gazzettaufficiale.it and aifa.gov.it. | Medium | Resolved | General | No
GAP003 | Data Gap | AEMPS (Spain) dates confirmed: Both Enhertu and Trodelvy approved by CIPM on same date, 28 Oct 2022. Sourced from Spanish Ministry of Health press release. | Medium | Resolved | General | No
GAP004 | Data Gap | G-BA AMNOG dates confirmed: Enhertu Beschluss 2 Feb 2023 (procedure D-836), Trodelvy Beschluss 19 May 2022 (procedure D-750). Sourced from g-ba.de. | Low | Resolved | General | No
GAP005 | Data Gap | ESMO guideline dates confirmed: Both Enhertu and Trodelvy included in ESMO mBC CPG published 19 Oct 2021 (Annals of Oncology). This predates Enhertu FDA full approval (Aug 2022) — the guideline referenced DESTINY-Breast03 data pre-approval. | Low | Resolved | General | No
S001 | Strategic | Trodelvy's Category 1 preferred NCCN status and broader 1L population coverage (CPS<10 AND CPS>=10) gives it a competitive advantage over Dato-DXd at launch. | High | Active | General | No
S002 | Strategic | Both ADCs have NCCN recommendations ahead of regulatory approval — unusual precedent that may accelerate SoC integration in US. | High | Active | General | No

## Enrollment Implications
Corcept Phase 3 Enrollment Implications
Analysis date: 15 Apr 2026. SoC integration = guideline inclusion + national reimbursement/access.
|  | Trodelvy 1L CPS<10 (ASCENT-03) |  | Trodelvy 1L CPS>=10 (ASCENT-04) |  | Dato-DXd 1L CPS<10 (TB02) |  | Dato-DXd 1L CPS>=10 (TB05)
Geography | HTA Body | SoC Date (Base) | Enrollment Window | SoC Date (Base) | Enrollment Window | SoC Date (Base) | Enrollment Window | SoC Date (Base) | Enrollment Window
US | N/A (Commercial) | Q4 2026 | Narrow (6mo) — prioritize now | Q4 2026 | Narrow (7mo) — prioritize now | Q3 2026 | Narrow (3mo) — prioritize now | Q1 2029 | Extended (34mo) — flexible timing
UK | NICE | Q2 2028 | Extended (25mo) — flexible timing | Q2 2028 | Extended (26mo) — flexible timing | Q1 2028 | Moderate (22mo) — plan enrollment | Q3 2030 | Extended (53mo) — flexible timing
France | HAS (Transparency Committee) | Q2 2027 | Moderate (14mo) — plan enrollment | Q3 2027 | Moderate (15mo) — plan enrollment | Q1 2027 | Narrow (11mo) — prioritize now | Q4 2029 | Extended (42mo) — flexible timing
Germany | G-BA (AMNOG) | Q1 2027 | Narrow (11mo) — prioritize now | Q2 2027 | Narrow (12mo) — prioritize now | Q3 2026 | Narrow (5mo) — prioritize now | Q3 2029 | Extended (39mo) — flexible timing
Italy | AIFA | Q4 2027 | Moderate (18mo) — plan enrollment | Q4 2027 | Moderate (19mo) — plan enrollment | Q3 2027 | Moderate (15mo) — plan enrollment | Q1 2030 | Extended (46mo) — flexible timing
Spain | AEMPS / IPT | Q3 2027 | Moderate (15mo) — plan enrollment | Q3 2027 | Moderate (16mo) — plan enrollment | Q2 2027 | Narrow (12mo) — prioritize now | Q4 2029 | Extended (43mo) — flexible timing
Canada | CADTH / pCODR | Q4 2027 | Moderate (19mo) — plan enrollment | Q4 2027 | Moderate (20mo) — plan enrollment | Q3 2027 | Moderate (16mo) — plan enrollment | Q1 2030 | Extended (47mo) — flexible timing
Key Findings
US: NCCN already includes both Trodelvy and Dato-DXd pre-approval. SoC integration will occur at commercial launch (H2 2026).
Germany: Access available at EMA approval (free pricing period). Among earliest EU5 markets for SoC shift.
UK: NICE CDF pathway likely for newer ADCs. Full SoC integration may lag 12-28 months post-FDA.
France/Italy/Spain: Longest reimbursement timelines (12-27 months post-FDA). Extended enrollment windows.
Canada: Moderate timeline. CADTH recommendation typically 12-20 months post-FDA.
Dato-DXd CPS>=10 (TROPION-Breast05): Significantly behind — PCD ~Oct 2027, FDA ~2029. Extended window in all markets.
Implication: Geographies with longer HTA timelines (IT, ES, FR) offer wider pre-SoC enrollment windows for Corcept's Phase 3.